## Product Backlog
ID | Story Title | User Story | Acceptance Criteria | Business Value | Estimation | Status
1 | Developement / Create classes that are required | As a Developer, I want to have an environment where Main, Game, Player, CPU, Human Player, Deck classes are in place and working as expected. | Every classes are initialy implemented with fields and methods using the UML diagram | 100 | 4 | In progress
2 | Developement / Create package with cards images | As a Developer, I want to have package with every card in spearate file. | Every card file is located in package | 100 | 2 | Done
3 | Developement / Create enum classes for Suit | As a Developer, I want to see enum classes used for the suit of a Card. | Enum instances are used everywhere instead of integers. | 200 | 2 | Not done
4 | Developement / Create UML diagram | As a Developer, I want to see UML diagram. | Completed UML diagram with acces modifiers, fields and methonds. | 400 | 6 | In progress
5 | Developement / Implement Main class | As a Developer, I want to see every function in class implemented. | Every element from UML is implemented. | 300 | 2018-02-01 | Not done
6 | Developent / Implement Game class | As a Developer, I want to see every function in class implemented. | Every element from UML is implemented. | 300 | 4 | Not done
7 | Developement / Implement Deck class | As a Developer, I want to see every function in class implemented. | Every element from UML is implemented. | 300 | 2 | Not done
8 | Developement / Implement Player abstract class with inherited classes | As a Developer, I want to see every function in class implemented. | Every element from UML is implemented. | 300 | 3 | Not done
9 | Developement / Implement Card class | As a Developer, I want to see every function in class implemented. | Every element from UML is implemented. | 300 | 2 | Not done
10 | Developement / Create ASCII pictures | As a Developer, I want to see every ASCII pictures in package | ASCII cards picture, winning picture and menu picture | 200 | 5 | In progress

## Sprint 1 Backlog
Story ID | Task ID | Task Description | Estimation | Responsible | Status |  | Monday | Tuesday | Wednesday | Thursday | Friday | Demo
1 | 1 | Initial implementation every class | 4 | Paweł | Done | Ideal | 30 | 22.5 | 15 | 7.5 | 0 | 0
2 | 2 | Create package with card images | 2 | Seweryn | In progress | Remaining | 30 | 25 | 19 | 10 | 0 | 0
3 | 3 | Create Suit enum class | 2 | Michał | Not done
4 | 4 | Create UML diagram | 6 | Michał | In progress
5 | 5 | Implement functions in Main class | 2018-02-01 |  | In progress
6 | 6 | Implement functions in Game class | 4 |  | In progress
7 | 7 | Implement functions in Deck class | 2 |  | In progress
8 | 8 | Implement functions in Player, CPU and HumanPlayer class | 3 |  | In progress
9 | 9 | Implement functions in Card class | 2 |  | In progress
10 | 10 | Create ASCII pictures | 5 |  | In progress